## Sheet1
Site | Phase | Cell Type | Cell | Test Case | Test ID | Scope | Status | Last modified | Modified User | VT Volume | VT Start DateTime | VT End DateTime | CH Volume | CH Date
BRH | Phase 1 | AIB | AIB101 | Depal | AIB-1001 | Cell | PASS | 8/4/2025, 11:43:12 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | BSSR | AIB-1002 | Cell | PASS | 8/4/2025, 11:43:13 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | Case Tipper | AIB-1003 | Cell | PASS | 8/4/2025, 11:43:15 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | CIS | AIB-1004 | Cell | PASS | 8/4/2025, 11:43:17 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | Reject line | AIB-1005 | Cell | PASS | 8/4/2025, 11:43:04 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | E-Stop | SA-1001 | Safety | BLOCKED | 8/4/2025, 11:43:07 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | Interlocks | SA-1002 | Safety | PASS | 8/4/2025, 11:43:09 PM | Test Engineer
BRH | Phase 1 | AIB | AIB101 | Cell Hardening - 1 | CH-1001 | Cell | DATA_ENTRY | 8/4/2025, 11:43:01 PM | Test Engineer |  |  |  | 32 | 2025-08-02
BRH | Phase 1 | AIB | AIB101 | Cell Hardening - 2 | CH-1002 | Cell | DATA_ENTRY | 8/4/2025, 11:42:59 PM | Test Engineer |  |  |  | 4435 | 2025-08-03
BRH | Phase 1 | AIB | AIB101 | Cell Hardening - 3 | CH-1003 | Cell | DATA_ENTRY | 8/4/2025, 11:42:57 PM | Test Engineer |  |  |  | 423 | 2025-08-04
BRH | Phase 1 | AIB | AIB101 | Volume Test | VT-0001 | Cell | FAIL | 8/4/2025, 11:43:06 PM | Test Engineer | 3234 | 2025-08-03T23:42 | 2025-08-03T21:42
BRH | Phase 1 | AOB | AOB102 | Case Labeler | AOB-1001 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Case Labeler - D1 | AOB-1002 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Case Labeler - D2 | AOB-1003 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Manual Palletization | AOB-1004 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Fallen Case | AOB-1005 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | PBA | AOB-1006 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Pallet PNA | AOB-1007 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Backup printer | AOB-1008 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB102 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Case Labeler | AOB-1001 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Case Labeler - D1 | AOB-1002 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Case Labeler - D2 | AOB-1003 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Manual Palletization | AOB-1004 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Fallen Case | AOB-1005 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | PBA | AOB-1006 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Pallet PNA | AOB-1007 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Backup printer | AOB-1008 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | AOB103 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AIB | SYSTEM | Messaging | AIB-SYS-101 | System | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AIB | SYSTEM | LPN | AIB-SYS-102 | System | NOT RUN | 8/4/2025, 11:40:32 PM
BRH | Phase 1 | AOB | SYSTEM | Messaging | AOB-SYS-101 | System | NOT RUN | 8/4/2025, 11:40:32 PM
MID | Phase 2 | AIB | AIB201 | Depal | AIB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | BSSR | AIB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | Case Tipper | AIB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | CIS | AIB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | Reject line | AIB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | AIB201 | Cell Hardening - 1 | CH-1001 | Cell | DATA_ENTRY | 8/4/2025, 11:44:08 PM | Test Engineer |  |  |  | 32 | 2025-08-01
MID | Phase 2 | AIB | AIB201 | Cell Hardening - 2 | CH-1002 | Cell | DATA_ENTRY | 8/4/2025, 11:48:55 PM | Test Engineer |  |  |  | 343 | 2025-08-02
MID | Phase 2 | AIB | AIB201 | Cell Hardening - 3 | CH-1003 | Cell | DATA_ENTRY | 8/4/2025, 11:48:57 PM | Test Engineer |  |  |  | 2433 | 2025-08-03
MID | Phase 2 | AIB | AIB201 | Volume Test | VT-0001 | Cell | DATA_ENTRY | 8/4/2025, 11:49:05 PM | Test Engineer | 4234 | 2025-08-03T23:49 | 2025-08-03T18:49
MID | Phase 2 | AOB | AOB202 | Case Labeler | AOB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Case Labeler - D1 | AOB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Case Labeler - D2 | AOB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Manual Palletization | AOB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Fallen Case | AOB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | PBA | AOB-1006 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Pallet PNA | AOB-1007 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Backup printer | AOB-1008 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB202 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Case Labeler | AOB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Case Labeler - D1 | AOB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Case Labeler - D2 | AOB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Manual Palletization | AOB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Fallen Case | AOB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | PBA | AOB-1006 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Pallet PNA | AOB-1007 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Backup printer | AOB-1008 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | AOB203 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | GAC | FLIB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Switch table | FLIB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Length | FLIB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Width | FLIB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Height | FLIB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Extendable E-stop | SA-1003 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB1 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | GAC | FLIB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Switch table | FLIB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Length | FLIB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Width | FLIB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Height | FLIB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Extendable E-stop | SA-1003 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB2 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | GAC | FLIB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Switch table | FLIB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Length | FLIB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Width | FLIB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Height | FLIB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Extendable E-stop | SA-1003 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Cell Hardening - 1 | CH-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | FLIB3 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | GAC | MCPIB-1001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Switch table | MCPIB-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Length | MCPIB-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Width | MCPIB-1004 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Height | MCPIB-1005 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | CIS | MCPIB-1006 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Pallet lift | MCPIB-1007 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | E-Stop | SA-1001 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Interlocks | SA-1002 | Safety | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Cell Hardening - 1 | CH-1001 | Cell | DATA_ENTRY | 1/20/2025, 4:00:00 AM | Test User |  |  |  | 9999 | 2025-01-20
MID | Phase 2 | MCPIB | MCPIB1 | Cell Hardening - 2 | CH-1002 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Cell Hardening - 3 | CH-1003 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | MCPIB | MCPIB1 | Volume Test | VT-0001 | Cell | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | SYSTEM | Messaging | AIB-SYS-101 | System | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AIB | SYSTEM | LPN | AIB-SYS-102 | System | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | AOB | SYSTEM | Messaging | AOB-SYS-101 | System | NOT RUN | 8/4/2025, 11:41:33 PM
MID | Phase 2 | FLIB | SYSTEM | Messaging | FLIB-SYS-101 | System | NOT RUN | 8/4/2025, 11:41:33 PM